## Sheet1
Activity | Start Date | End Date | Duration (days)
Project Proposal |  |  | 40
Discuss proposal with supervisor | 2022-01-15 | 2022-01-17 | 6
Write project proposal | 2022-01-18 | 2022-01-29 | 12
Upload project proposal | 2022-01-30 | 2022-01-31 | 2
The proposed discussion has been edited with the supervisor | 2022-02-01 | 2022-02-08 | 8
Revise project proposal | 2022-02-09 | 2022-02-14 | 6
Upload revise project proposal | 2022-02-15 | 2022-02-20 | 6
Initial report |  |  | 60
Research and learn about social websites | 2022-03-26 | 2022-03-26 | 1
Research and learn about music websites | 2022-03-27 | 2022-03-27 | 1
Learn and research the steps of buiding a complete | 2022-03-28 | 2022-03-30 | 3
Plan the steps of building social media website | 2022-03-31 | 2022-04-02 | 3
Learn the basics and depth of ReactJS | 2022-04-03 | 2022-04-12 | 10
Research on ReactJS related technologies | 2022-04-13 | 2022-04-21 | 9
Learn the basics and depth of NodeJS | 2022-04-22 | 2022-05-01 | 10
Research on NodeJS related technologies | 2022-05-02 | 2022-05-10 | 9
Study how NodeJS and ReactJS work on the server | 2022-05-11 | 2022-05-14 | 4
Study methods of saving system data | 2022-05-15 | 2022-05-17 | 3
Learn about user interfaces on social networking sites | 2022-05-18 | 2022-05-19 | 2
Find out information related to posting music on the website | 2022-05-20 | 2022-05-21 | 2
Find out users 's music entertainment trends | 2022-05-22 | 2022-05-23 | 2
Upload initial report | 2022-05-24 | 2022-05-24 | 1
Project implementation |  |  | 55
Register domain name and buy hosting | 2022-05-30 | 2022-06-02 | 4
Up ideas and methods of operation for the website | 2022-06-03 | 2022-06-08 | 6
Database building | 2022-06-09 | 2022-06-15 | 7
Functional design for the website | 2022-06-16 | 2022-07-01 | 16
Interface design for the website | 2022-07-02 | 2022-07-15 | 14
Deploy website on server | 2022-07-16 | 2022-07-18 | 3
Testing and fix website errors | 2022-07-19 | 2022-07-23 | 5
Interim report |  |  | 15
Prepare interim report | 2022-07-29 | 2022-08-11 | 14
Upload interim report | 2022-08-12 | 2022-08-12 | 1
Final report |  |  | 45
Prepare final report | 2022-08-18 | 2022-09-30 | 44
Upload final report | 2022-10-01 | 2022-10-01 | 1
Project demonstration |  |  | 45
Prepare for demonstration | 2022-10-07 | 2022-11-20 | 45